## Sheet1
Yahtzee_4
Incomplete | % Complete
Name | Task | 3/19 - 3/25 |  | 3-25 - 3/31 | 4/1 - 4/8 |  | 4/9 - 4/15 |  |  | 4/16-4/24
Danielle | User class | 90 %
Danielle | Admin class | 90 %
Danielle | Game flow - Controlling rounds & which player's turn in main | 60 %
Danielle | Gantt Chart | 40%
Danielle/Ismael | Weekly Group Write up | 50%
Ismael | UML Chart | 50%
Ismael | Scorecard class. 1 round working for 1 player | 10%
Ismael/Logan | Dice class | 5%
Logan | Flowchart | 50%
Amir | Style scorecard print out | 0%
Ismael/Logan/Danielle | Merge Scorecard & Dice |  |  |  |  | 0%
Danielle | Merge User & game flow(round+player) |  |  |  |  | 0%
Danielle/Ismael | Merge User & Scorecard |  |  |  |  | 0%
Everyone | Start documentation | [6 empty] | 0%
Everyone | Plan presentation | [7 empty] | 0%
Everyone hopefully | Finalize documentation |  | 10 %
Everyone | Practice presentation | [9 empty] | 0%