## Sheet1
Yahtzee_4
Incomplete | % Complete
Name | Task | 3/19 - 3/25 |  | 3-25 - 3/31 |  | 4/1 - 4/8 |  | 4/9 - 4/15 |  |  | 4/16-4/24
Danielle | User class | 100 %
Danielle | Admin class | 95 %
Danielle | Game flow - round & player control | 100 %
Danielle | Gantt Chart | 70%
Danielle/Ismael | Weekly Group Write up | 70%
Ismael | UML Chart | 50%
Ismael | Scorecard class. 1 round working for 1 player | 90%
Ismael/Logan | Dice class | 100%
Logan | Flowchart | 100%
Ismael | Style scorecard print out | 100%
Danielle | Merge game flow(round+player control) to main.cpp |  |  |  | 70%
Danielle/Ismael | Merge User & Scorecard |  |  |  |  | 80%
Logan/Danielle | Compose to-do list for documentation | [7 empty] | 0%
Logan/Everyone | Start documentation | [7 empty] | 0%
Everyone | Plan presentation | [8 empty] | 0%
Everyone hopefully | Finalize documentation |  | 10 %
Everyone | Practice presentation | [10 empty] | 0%
Logan | Style html page with game's name & scorecard | [5 empty] | 0%
Danielle | DRY. Clean up repeative code in Admin & User | [6 empty] | 10%